## Tabelle1
Milestone | Start | End | Resp. | 15.03. | 22.03. | 29.03. | 05.04. | 12.04. | 19.04. | 26.04. | 03.05. | 10.05. | 17.05. | 24.05. | 31.05. | 07.06. | 14.06.
Circuit diagram | 15.03. | 22.03. | JB
Bluetooth-connection with "Hello World" | 19.03. | 29.03. | JB
Serial transmission of data | 15.03. | 29.03. | JB
Bluetooth-transmission of data | 22.03. | 29.03. | JB
Set `WorkMode` | 29.03. | 12.04. | JB
`setup.exe` + ID | 05.04. | 26.04. | JB
control LED + blinking modus for errors | 19.04. | 26.04. | JB
Recieves "Hello World" from `Tempera` and sends to backend. Recognizes `Tempera` as BLE-Device. | 19.03. | 29.03. | AR
Database for interim storage of data | 15.03. | 29.03. | AR
Recieves data from `Tempera` | 29.03. | 12.04. | AR
Sends data to backend in regular time intervals | 05.04. | 19.04. | AR
Logging and warnings (on sensor errors) | 19.04. | 26.04. | AR
Installation of `Accesspoint` via `./configure` script for admin | 19.04. | 10.05. | AR
Implement classdiagram in `model` | 15.03. | 22.03. | MN
Manager role including management of `Project` and `Group` and analysis of working hours. | 15.03. | 29.03. | LH & NS
REST Interface for data receive from `Accesspoint` | 22.03. | 29.03. | MN & NS
Administration of `TemperaDevice`, `Accesspoint`, `Room`, `User` and `Limit` (administrator role) | 29.03. | 12.04. | LH
Display of climate data in `ui` as tables and graphs (including filtering and sorting) | 29.03. | 12.04. | LH
Recording and editing of working hours | 12.04. | 26.04. | MN & NS
Display of working hours in `ui` as tables and graphs (including filtering and sorting). | 12.04. | 26.04. | LH
Handling of limit transgression and warnings | 26.04. | 10.05. | MN & NS
Logging | 03.05. | 10.05. | MN
Deletion policies | 10.05. | 17.05. | NS
UI | 17.05. | 24.05. | LH
`JavaDoc` documentation | 15.03. | 31.05.
Unit-, componentn- and system-tests | 15.03. | 31.05.
Interim Presentation | 17.05. | 24.05.
Testbook and acceptance testing + Software ready for testing | 24.05. | 31.05.
Documentation of acceptance testing of other team | 31.05. | 07.06.
Software Revision | 07.06. | 14.06.
Final Testing and Documentation | 14.06. | 21.06.
Final report and presentation including Software concept paper | 14.06. | 21.06.